## Sheet1
The project will be completed over two semesters: September–December 2026 and January–May 2027. | [11 empty] | Key milestones | Description | Date
Capstone Project 2026-2027 | [11 empty] | ◆ M1 | Proposal submitted | 2026-10-25
TASK | START | END | 1st Semestre 2026 |  |  |  | 2nd Semestre 2027 |  |  |  |  | ◆ M2 | Data preparation completed ( | 2027-01-23
|  |  | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | ◆ M3 | Models developed | 2027-03-30
Business Problem & literature review | 2026-09-28 | 2026-10-05 | [9 empty] | ◆ M4 | Model evaluation completed | 2027-04-30 | bar: 2026-09-01 to 2026-10-01
Dataset selection and validation | 2026-10-05 | 2026-10-09 | [9 empty] | ◆ M5 | Final submission | 2027-05-30 | bar: 2026-09-01 to 2026-10-01
Define business problem and objectives | 2026-10-09 | 2026-10-12 | bar: 2026-09-01 to 2026-10-01
Define Methodology, Scope | 2026-10-12 | 2026-10-25 | bar: 2026-09-01 to 2026-10-01
◆ M1 — Proposal submitted | 2026-10-25 | 2026-10-25 | bar: 2026-10-01
Dataset exploration and analysis | 2026-10-25 | 2026-11-24 | bar: 2026-10-01 to 2026-11-01
Data cleaning and preparation | 2026-11-24 | 2026-12-24 | bar: 2026-11-01 to 2026-12-01
Feature selection and engineering | 2026-12-24 | 2027-01-23 | bar: 2026-12-01 to 2027-01-01
◆ M2 — Data preparation completed | 2027-01-23 | 2027-01-23 | bar: 2027-01-01
ML model development | 2027-01-24 | 2027-03-30 | bar: 2027-01-01 to 2027-03-01
◆ M3 — Models developed | 2027-03-30 | 2027-03-30 | bar: 2027-03-01
Model evaluation and comparison | 2027-03-30 | 2027-04-30 | bar: 2027-03-01 to 2027-04-01
◆ M4 — Evaluation completed | 2027-04-30 | 2027-04-30 | bar: 2027-04-01
Tableau dashboard | 2027-04-30 | 2027-05-10 | bar: 2027-04-01 to 2027-05-01
Business recommendations | 2027-04-30 | 2027-05-10 | bar: 2027-04-01 to 2027-05-01
Final report | 2027-05-10 | 2027-05-30 | bar: 2027-05-01
◆ M5 — Final submission | 2027-05-30 | 2027-05-30 | bar: 2027-05-01
Key milestones | Description | Date
◆ M1 | Proposal submitted | 2026-10-25
◆ M2 | Data preparation completed | 2027-01-23
◆ M3 | Models developed | 2027-03-30
◆ M4 | Model evaluation completed | 2027-04-30
◆ M5 | Final submission | 2027-05-30

## Sheet2
Key milestones | Description | Date
◆ M1 | Proposal submitted | 2026-10-25
◆ M2 | Data preparation completed ( | 2027-01-23
◆ M3 | Models developed | 2027-03-30
◆ M4 | Model evaluation completed | 2027-04-30
◆ M5 | Final submission | 2027-05-30